## Tabelle1
Activity Plan Group 5 |  |  |  | Date: | 2017-09-01
|  |  | Status options + definition | open | The responsible person hasn't started with the activity jet
|  |  |  | in progress | The responsible person is working on this activity
|  |  |  | waiting | The responsible person has to wait for someonle else to start or continue the activity
|  |  |  | done | The activity is finished
|  |  |  | delay | The activity is on delay
ID | Activity2 | Definition and Subtask | Responsible Person | Status | Due Date | Start Date | End Date | Comment
1 | Project Plan |  |  | open
2 | Risk Management | Risk Register; Impact |  | open |  |  |  | Risk Register created but still empty
3 | Communication Management | List of Stakeholders, Communication Plan |  | open
4 | Quality Plan | Definition of Done; Quality standards |  | open |  |  |  | document created but still empty; just framework
5 | Testing Plan |  |  | open
6 | Competences |  |  | open
7 | Roles |  |  | done |  |  |  | roles declared
8 | SRS | backlog |  | open
9 | Self competences | for each Student individual |  | open
10 | Configuration Management Plan |  |  | open
11 | Time tracking Report / Member |  |  | open